## Instructions
How to successfully use this Gantt Chart / Schedule Overview
Step 1: Save this document using the "Save As" tool. Do not save your work on the main template.
Step 2: Build your Schedule overview using the "Schedule Overview" Tab.
Step 3: ALL Cells in bright yellow need to be filled out.
● Project Title: Type the title of your project
● StartDate: Type the start date of your project. Example: 8/24/2011
● Gantt Start: MUST start on a Monday. Example: If the project starts on 8/24/2011, put 8/22/2011 in the GanntStart cell because that is the Monday before the project starts.
Step 4: Do NOT delete the "Schedule Overview " and "Holidays" tabs. The instructions tab may be deleted if not needed.
If you would like to link a Start Date to a different End Date:
1) Click on the Start Date Cell for the task you would like to change the reference. You should get something that looks similar to the following:
=WORKDAY(PrevEndDate,B30-C30,Holidays!A:A)
OR
=WORKDAY(LastEndDate,B30-C30,Holidays!A:A)
OR
=WORKDAY(REF!,B30-C30,Holidays!A:A)
2) Click on the equation in the formula bar for the Start and highlight only the equivalent of what PrevEndDate, LastEndDate or REF! represents in the above equation.
3) Once only PrevEndDate, LastEndDate , or REF! is highlighted in the formula bar, click on the End date that you would like to link your task to and press "enter." This should link your start date to a different end date.
Example: =WORKDAY(E24,B30-C30,Holidays!A:A)
● PrevEndDate: This is the default. It refers to the end date of the task before your current task.
● LastEndDate: This is put in all the start dates that are right after a phase line. These cells are also in orange. LastEndDate refers to the last end date in the phase before it, NOT the end date of the phase you are currently in.
● REF!: This only comes up when there is an error in your formula.
This document is password protected. If password protected changes need to be made, please remember that it may affect how the document functions.
Right click on this sheet's tab and select "unprotect sheet"
Password: viscira
(All lower case)
This is the Schedule Overview Template. Please read the instructions and see tabs below.
Other Information
● Only boxes in white should be changed. Other boxes in color are using formulas that shouldn't be touched.
● Do not touch the Gantt portion of the document. It is fully automated.
● Weekends and Viscira holidays are accounted for. You can't schedule someone to work over the weekend or holidays with this sheet. Holidays are in a separate tab. If you need to schedule someone to work over a holiday, you can simply remove that holiday date from the holiday tab.
Add or delete Holidays by clicking the "Holidays" tab and following the instructions listed there.
Column Descriptions
Back column:
● Positive #: Push start date back.
● Negative #: Push start date of the task into the future.
● 1 or More Days: Task will automatically start the next day from the previous row.
● Blank or "0" days : Task will start same day as previous row
Start Date & End Date: These will automatically populate, don't touch except for first date.
Days: The number of days a task, deliver, review is assigned for. If same day, leave blank or put in 0.
Hrs: automated column so you can see how many hours the days add up to if they were 8 hr days.
Add: If a task is running over the days or if the client is taking longer than expected to review something. Don't change the days column, just add extra days in the add column to make the start date of the next step line up.
You must copy the whole line!
Select the row. Do this by selecting the number of the row on the far left of this document. This should highlight the entire row. Copy (Control + C) and paste (Control + P) the proper row color to your document.
Key
Red: All Deliveries (Should only be 0 -1 days)
Blue: Reviews, Client approvals / Med Reg / Anytime client is responsible for a part of the project
Green line (Black text): Any work Viscira is responsible for
Orange: What stage are we in the 5 step process? Discover, Design, Develop, Deploy, Debrief. The start date should equal the cell right below it. The end date should equal the last date in the phase.

## Schedule Overview
Today's Date
2013-05-30
|  | Back | Start Date | End Date | Days | hrs | Add | [5 empty] | 1900-01-06 |  |  |  |  | 1900-01-13 |  |  |  |  | 1900-01-20 |  |  |  |  | 1900-01-27 |  |  |  |  | 1900-02-03 |  |  |  |  | 1900-02-10 |  |  |  |  | 1900-02-17 |  |  |  |  | 1900-02-24 |  |  |  |  | 1900-03-03 |  |  |  |  | 1900-03-10 |  |  |  |  | 1900-03-17 |  |  |  |  | 1900-03-24 |  |  |  |  | 1900-03-31 |  |  |  |  | 1900-04-07 |  |  |  |  | 1900-04-14 |  |  |  |  | 1900-04-21 |  |  |  |  | 1900-04-28 |  |  |  |  | 1900-05-05 |  |  |  |  | 1900-05-12 |  |  |  |  | 1900-05-19 |  |  |  |  | 1900-05-26 |  |  |  |  | 1900-06-02 |  |  |  |  | 1900-06-09 |  |  |  |  | 1900-06-16 |  |  |  |  | 1900-06-23 |  |  |  |  | 1900-06-30 |  |  |  |  | 1900-07-07 |  |  |  |  | 1900-07-14 |  |  |  |  | 1900-07-21 |  |  |  |  | 1900-07-28 |  |  |  |  | 1900-08-04 |  |  |  |  | 1900-08-11 |  |  |  |  | 1900-08-18 |  |  |  |  | 1900-08-25 |  |  |  |  | 1900-09-01 |  |  |  |  | 1900-09-08 |  |  |  |  | 1900-09-15 |  |  |  |  | 1900-09-22 |  |  |  |  | 1900-09-29 |  |  |  |  | 1900-10-06 |  |  |  |  | 1900-10-13 |  |  |  |  | 1900-10-20 |  |  |  |  | 1900-10-27 |  |  |  |  | 1900-11-03 |  |  |  |  | 1900-11-10 |  |  |  |  | 1900-11-17 |  |  |  |  | 1900-11-24 |  |  |  |  | 1900-12-01 |  |  |  |  | 1900-12-08 |  |  |  |  | 1900-12-15 |  |  |  |  | 1900-12-22 |  |  |  |  | 1900-12-29 |  |  |  |  | 1901-01-05 |  |  |  |  | 1901-01-12 |  |  |  |  | 1901-01-19 |  |  |  |  | 1901-01-26 |  |  |  |  | 1901-02-02 |  |  |  |  | 1901-02-09 |  |  |  |  | 1901-02-16 |  |  |  |  | 1901-02-23 |  |  |  |  | 1901-03-02 |  |  |  |  | 1901-03-09 |  |  |  |  | 1901-03-16 |  |  |  |  | 1901-03-23 |  |  |  |  | 1901-03-30 |  |  |  |  | 1901-04-06 |  |  |  |  | 1901-04-13 |  |  |  |  | 1901-04-20 |  |  |  |  | 1901-04-27 |  |  |  |  | 1901-05-04 |  |  |  |  | 1901-05-11
 | time axis 0 to 1901-05-15
Discover |  |  | 0 | 1900-01-25 | 20 | 160 | bar: 0 to 1900-01-24
Task | 1 |  |  | 1900-01-08 | 7 | 56
Delivery | 1 |  | 1900-01-09 | 1900-01-09 | 1 | 8 | bar: 1900-01-09
Review | 1 |  | 1900-01-10 | 1900-01-12 | 3 | 24 | bar: 1900-01-10
Task | 1 |  | 1900-01-15 | 1900-01-19 | 5 | 40 | bar: 1900-01-15 to 1900-01-17
Delivery | 1 |  | 1900-01-22 | 1900-01-22 | 1 | 8 | bar: 1900-01-22
Review | 1 |  | 1900-01-23 | 1900-01-25 | 3 | 24 | bar: 1900-01-23 to 1900-01-24
Design |  |  | 1900-01-26 | 1900-03-20 | 15 | 120 | bar: 1900-01-27 to 1900-03-20
Task | 1 |  | 1900-01-26 | 1900-02-01 | 5 | 40 | bar: 1900-01-27 to 1900-01-31
Delivery | 1 |  | 1900-02-02 | 1900-02-02 | 1 | 8
Review | 1 |  | 1900-02-05 | 1900-02-07 | 3 | 24 | bar: 1900-02-05 to 1900-02-07
Task | 1 |  | 1900-02-08 | 1900-02-14 | 5 | 40 | bar: 1900-02-10 to 1900-02-14
Delivery | 1 |  | 1900-02-15 | 1900-02-15 | 1 | 8
Review | 1 |  | 1900-02-16 | 1900-02-20 | 3 | 24 | bar: 1900-02-17 to 1900-02-20
Task | 1 |  | 1900-02-21 | 1900-02-27 | 5 | 40 | bar: 1900-02-21 to 1900-02-27
Delivery | 1 |  | 1900-02-28 | 1900-02-28 | 1 | 8 | bar: 1900-02-28
Review | 1 |  | 1900-03-01 | 1900-03-05 | 3 | 24 | bar: 1900-03-03 to 1900-03-05
Task | 1 |  | 1900-03-06 | 1900-03-12 | 5 | 40 | bar: 1900-03-06 to 1900-03-12
Delivery | 1 |  | 1900-03-13 | 1900-03-13 | 1 | 8 | bar: 1900-03-13
Review | 1 |  | 1900-03-14 | 1900-03-20 | 5 | 40 | bar: 1900-03-14 to 1900-03-20
Develop |  |  | 1900-03-21 | 1900-05-09 | 15 | 120 | bar: 1900-03-21 to 1900-05-09
Task | 1 |  | 1900-03-21 | 1900-03-27 | 5 | 40 | bar: 1900-03-21 to 1900-03-27
Delivery | 1 |  | 1900-03-28 | 1900-03-28 | 1 | 8 | bar: 1900-03-28
Review | 1 |  | 1900-03-29 | 1900-04-02 | 3 | 24 | bar: 1900-03-31 to 1900-04-02
Task | 1 |  | 1900-04-03 | 1900-04-09 | 5 | 40 | bar: 1900-04-03 to 1900-04-09
Delivery | 1 |  | 1900-04-10 | 1900-04-10 | 1 | 8 | bar: 1900-04-10
Review | 1 |  | 1900-04-11 | 1900-04-13 | 3 | 24 | bar: 1900-04-11
Task | 1 |  | 1900-04-16 | 1900-04-20 | 5 | 40 | bar: 1900-04-16 to 1900-04-18
Delivery | 1 |  | 1900-04-23 | 1900-04-23 | 1 | 8 | bar: 1900-04-23
Review | 1 |  | 1900-04-24 | 1900-04-26 | 3 | 24 | bar: 1900-04-24 to 1900-04-25
Task | 1 |  | 1900-04-27 | 1900-05-03 | 5 | 40 | bar: 1900-04-28 to 1900-05-02
Delivery | 1 |  | 1900-05-04 | 1900-05-04 | 1 | 8
Review | 1 |  | 1900-05-07 | 1900-05-09 | 3 | 24 | bar: 1900-05-07 to 1900-05-09
Deploy |  |  | 1900-05-10 | 1900-06-04 | 15 | 120 | bar: 1900-05-12 to 1900-06-04
Task | 1 |  | 1900-05-10 | 1900-05-16 | 5 | 40 | bar: 1900-05-12 to 1900-05-16
Delivery | 1 |  | 1900-05-17 | 1900-05-17 | 1 | 8
Review | 1 |  | 1900-05-18 | 1900-05-22 | 3 | 24 | bar: 1900-05-19 to 1900-05-22
Task | 1 |  | 1900-05-23 | 1900-05-29 | 5 | 40 | bar: 1900-05-23 to 1900-05-29
Delivery | 1 |  | 1900-05-30 | 1900-05-30 | 1 | 8 | bar: 1900-05-30
Review | 1 |  | 1900-05-31 | 1900-06-04 | 3 | 24 | bar: 1900-06-02 to 1900-06-04
Debrief |  |  | 1900-06-05 | 1900-06-15 | 9 | 72 | bar: 1900-06-05 to 1900-06-13
Task | 1 |  | 1900-06-05 | 1900-06-11 | 5 | 40 | bar: 1900-06-05 to 1900-06-11
Delivery | 1 |  | 1900-06-12 | 1900-06-12 | 1 | 8 | bar: 1900-06-12
Review | 1 |  | 1900-06-13 | 1900-06-15 | 3 | 24 | bar: 1900-06-13

## Holidays
2013-01-01
2013-02-18
2013-05-27
2013-07-04
2013-07-05
2013-09-02
2013-11-28
2013-11-29
2013-12-25
2013-12-26
2013-12-27
2013-12-30
2013-12-31
2014-01-01
This sheet is password protected.
Only modify this sheet if Holidays need to be added. List Holidays in Column A , as shown here. To unprotect sheet, right click on this sheet's tab and select "unprotect sheet." Fill in the password listed below.
Password: viscira
(All lower case)